## Aug 2018
August 2018
Example Tasks |  | Notes
Update contact information for grant leaders and send to Adam Collins: Collins_A@cde.state.co.us
Implementation Coach
Other school/district contacts that may have turned over since the previous year
Bullying Prevention Committee
Hold first BPC meeting
Define roles, responsibilities, and norms for the BPC
Discuss membership attrition and additions
Discuss purpose of the grant
Calendar for meetings (at least monthly)
Review progress from last year and goals developed for current year
School Climate and Culture
Review/Define school-wide behavioral expectations
Post/review behavioral expectations in all school settings
Establish/review common responses to problem behaviors
Establish/review common area supervision staff’s supervision techniques
Bullying Prevention Curriculum
Ensure new staff have received or scheduled training on the bullying prevention curriculum
Remind staff of the procedures for two-way communication with the BPC about implementation of the curriculum
Provide staff with an implementation schedule for the bullying prevention curriculum
Review plan for measuring implementation fidelity
Surveys and Data
Review procedures for the documentation of bullying incidents reviewed at BPC meetings
Review procedures for reporting results from annual survey to stakeholders
Consider additional strategies for increasing the number of parent/guardian opt-in forms returned
Family, School, and Community Partnering
Review procedures for informing parents and community members about bullying prevention efforts at beginning of the year school events
Student Voice
Select student leadership to partner with adults for informing bullying prevention efforts, analyzing survey results, and partnering with staff to deliver bullying prevention best practices
Designate/Volunteer an adult leader to obtain student voice
Bullying Prevention Policy
Review with staff the district and school bullying prevention policy

## Sep 2018
September 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Solidify BPC membership and meeting dates
Complete BPEG Self-Assessment online
School Climate and Culture
Ensure procedures for supporting targets and perpetrators of bullying are in place
Ensure procedures and consequences for bullying behavior are in place
Bullying Prevention Curriculum
Ensure curriculum lessons are being implemented with fidelity
Discuss how coaching of teachers for program implementation will be delievered as necessary
Ensure new students and staff are oriented to the program
Surveys and Data
Ensure that incidents of bullying are systematically recorded to provide data for problem solving
Solicit and collect parent/guardian opt-in forms as needed
Review bullying incident data and develop a response as necessary
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Begin planning of parent education night about the BPEG and bullying prevention
Student Voice
Review bullying prevention data with student leaders
Gather input from students on how they would like to partner with staff to engage in bullying prevention best practices
Bullying Prevention Policy
Determine any need for revisions to the school bullying prevention policy

## Oct 2018
October 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents that have occurred since the start of the year
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Review bullying prevention data with student leaders
Begin having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed

## Nov 2018
November 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review progress on BPEG activities and discuss any necessary changes
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Conduct curriculum fidelity assessment
Surveys and Data
Review incidents of bullying and determine need for Tier 2/3 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Hold parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed

## Dec 2018
December 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Plan for the next semester's large agenda items (e.g., student survey, re-teaching behavior expectations in January)
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Get feedback from staff on their opinion of the curriculum
Review scores from last month's fidelity assessment
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed