## Instructions
School Bullying Prevention and Education Grant Year 3 Timeline
Instructions
The School Bullying Prevention and Education Grant (BPEG) Year 3 Timeline is designed to support BPEG grantees in prioritizing grant responsibilities. In the third year of the grant, it would be beneficial to refer back to the BPEG Self-Assessment to ensure your school(s) is moving forward with the work of the grant. This timeline is meant to be an example of possible bullying prevention grant activities. Each school should consider where it is related to grant activities and if additional items should be added to their timeline.
District:
School:
Date:

## Aug 2018
August 2018
Example Tasks |  | Notes
Update contact information for grant leaders and send to Adam Collins: Collins_A@cde.state.co.us
Implementation Coach
Other school/district contacts that may have turned over since the previous year
Bullying Prevention Committee
Hold first BPC meeting
Define roles, responsibilities, and norms for the BPC
Discuss membership attrition and additions
Discuss purpose of the grant
Calendar for meetings (at least monthly)
Review progress from last year and goals developed for current year
School Climate and Culture
Review/Define school-wide behavioral expectations including digital citizenship training for students
Post/review behavioral expectations in all school settings
Establish/review common responses to problem behaviors
Establish/review common area supervision staff’s supervision techniques
Bullying Prevention Curriculum
Ensure new staff have received or scheduled training on the bullying prevention curriculum
Remind staff of the procedures for two-way communication with the BPC about implementation of the curriculum
Provide staff with an implementation schedule for the bullying prevention curriculum
Review plan for measuring implementation fidelity
Surveys and Data
Review procedures for the documentation of incidents of bullying for review at BPC meetings
Review procedures for reporting results from annual survey to stakeholders
Consider additional strategies for increasing the number of parent/guardian opt-in forms returned
Family, School, and Community Partnering
Review procedures for informing parents and community members about bullying prevention efforts at beginning of the year school events
Student Voice
Select student leadership to partner with adults for informing bullying prevention efforts, analyzing survey results, and partnering with staff to deliver bullying prevention best practices
Designate/Volunteer an adult leader to obtain student voice
Bullying Prevention Policy
Review with staff the district and school bullying prevention policy

## Sep 2018
September 2018
Example Tasks |  | Notes
Cohort 2 RFP
Apply to be in the BPEG Cohort 2 (Anticipated early-to-mid September)
Bullying Prevention Committee
Hold BPC meeting
Solidify BPC membership and meeting dates
Complete BPEG Self-Assessment online
School Climate and Culture
Ensure procedures for supporting targets and perpetrators of bullying are in place
Ensure procedures and consequences for bullying behavior are in place
Bullying Prevention Curriculum
Ensure curriculum lessons are being implemented with fidelity
Discuss how coaching of teachers for program implementation will be delievered as necessary
Ensure new students and staff are oriented to the program
Surveys and Data
Ensure that incidents of bullying are systematically recorded to provide data for problem solving
Solicit and collect parent/guardian opt-in forms as needed
Review bullying incident data and develop a response as necessary
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Begin planning of parent education night about the BPEG and bullying prevention
Student Voice
Review bullying prevention data with student leaders
Gather input from students on how they would like to partner with staff to engage in bullying prevention best practices
Bullying Prevention Policy
Determine any need for revisions to the school bullying prevention policy
Reports
Annual Financial Report due September 30, 2018

## Oct 2018
October 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents that have occurred since the start of the year
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Review bullying prevention data with student leaders
Begin having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Implementation Coach Interim Report due October 5, 2018

## Nov 2018
November 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review progress on BPEG activities and discuss any necessary changes
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Conduct curriculum fidelity assessment
Surveys and Data
Review incidents of bullying and determine need for Tier 2/3 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Hold parent education night and get feedback on effectiveness
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed

## Dec 2018
December 2018
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Plan for the next semester's large agenda items (e.g., student survey, re-teaching behavior expectations in January)
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Get feedback from staff on their opinion of the curriculum
Review scores from last month's fidelity assessment
Surveys and Data
Review bullying incident reports for any patterns and problem solve solutions for the spring semester
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Review feedback from parent education night and consider changes for next year's November parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Interim Financial Report due December 1, 2018

## Jan 2019
January 2019
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents
Problem solve and action plan as appropriate based on first semester data
School Climate and Culture
Re-teach expected behaviors in specific settings
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented and/or followed up on with fidelity
Orient any new students and staff to the program
Get feedback from staff on their opinion of the curriculum
Review scores from last month's fidelity assessment
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Begin planning a spring semester parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Implementation Coach Interim Report due January 31, 2019

## Feb 2019
February 2019
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented and/or followed up on with fidelity
Orient any new students and staff to the program
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Communicate the date and time fo the annual survey to stakeholders
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Interim Financial Report due February 28, 2019

## Mar 2019
March 2019
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented and/or followed up on with fidelity
Orient any new students and staff to the program
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Finalize preparations for annual survey
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Final Budget Revisions due March 31, 2019

## Apr 2019
April 2019
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Review bullying incidents
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented and/or followed up on with fidelity
Orient any new students and staff to the program
Surveys and Data
Review incidents of bullying and determine need for Tier 2 supports as needed
Solicit and collect parent/guardian opt-in forms as needed
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Complete planning for parent education night
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Implementation Coach Interim Report due April 5, 2019

## May 2019
May 2019
Example Tasks |  | Notes
Bullying Prevention Committee
Hold BPC meeting
Complete BPEG Self-Assessment by end of May
School Climate and Culture
Orient any new students and staff to the behavior expectations, consequences, positive reinforcement system, etc.
Celebrate successes with stakeholders
Bullying Prevention Curriculum
Provide support as necessary to ensure curriculum lessons are being implemented with fidelity
Orient any new students and staff to the program
Get feedback from staff on their opinion of the curriculum
Review scores from last month's fidelity assessment
Surveys and Data
Ensure documentation of incidents of bullying from the year are systematically recorded to provide data for problem solving next year
Solicit and collect parent/guardian opt-in forms as needed
Administer annual survey by the end of May
Ensure parent/guardian opt-in forms are included in enrollment packets for the upcoming school year
Family, School, and Community Partnering
Ensure continued two-way communication between family, school, and community members
Student Voice
Continue having students partner with the implementation of bullying prevention best practices (e.g., administering lessons, creating videos of school rules)
Bullying Prevention Policy
Review bullying prevention policy as needed
Reports
Interim Financial Report due May 5, 2019

## Jun 2019
June 2019
Example Tasks |  | Notes
Reports
Annual Report due June 30, 2019