## School Leader Integrated Timeli
Quarter | Task Name | Description | Topic | Start | Finish | Duration | Predecessors | Assigned To | % Complete | Status | Comments
| Quarter One Actions |  |  | 2022-07-01 | 2022-09-30 | 66d
Accountability
Quarter 1 | Accountability Committee Involvement in UIP and Budget | Ensure School Accountability Committee is involved in revising the UIP and providing input on budgets. | Accountability | 2022-07-01 | 2023-06-30 | 261d
Quarter 1 | Preliminary Transitional Frameworks Release | Analyze preliminary 2019 School Transitional Frameworks (expected to be available to districts in late August for traditional schools; Mid-Sept release for AECs). | Accountability | 2022-09-02 | 2022-09-29 | 20d
Quarter 1 | Expected Request to Reconsider Window | Districts may provide additional evidence if they do not agree with the preliminary 2022 plan type or wish apply to exit the district/school from the accountability clock. New 90% total state participation rate threshold applies. | Accountability | 2022-08-24 | 2022-10-17 | 39d
Assessment
Quarter 1 | Identify School Assessment Coordinator and School Technology Coordinator | Ensure your school has an appointed school assessment coordinator and school technology coordinator. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Develop a Policy on How Parents May Excuse their child(ren) from the state assessments | LEPs: Adopt and implement a policy and implement LEP's procedure by which a student's parent(s) may excuse the student from participating in one or more of the state assessments. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Develop a Policy to Request Paper Form of State Assessment | LEPs: Adopt and implement a written policy by which the local education provider will decide whether to request the paper form of the state assessments. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Communicate Assessment Schedule | Distribute and post written information regarding the assessments to be administered during the school year inclduing an assessment calendar. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Share 2021 Individual State Assessment Results | Distribute 2022 state assessment results to educators and parents. Confidential individual student reports can be shared with parents as soon as they are available. Aggregated and individual student level results may be used internally for informational planning purposes before results are publicly released. | Assessment | 2022-06-17 | 2022-09-30 | 76d
Educator Effectiveness
Quarter 1 | Evaluation System Training for Educators New to Building | Provide a full and comprehensive training on the district's evaluation system to all new educators (i.e., teachers, SSPs, and assistant principals) in your building. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Orient Returning Educators on Educator Evaluation System Updates | Provide re-orientation/updates training for all licensed personnel (i.e., principals, assistant principals, teachers and special services providers [SSPs]) on the district's educator evaluation system and highlight any updates in process and/or measures of student learning/outcomes that will take place for the school year. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Engage and support educators' self-reflection for continued professional growth | Engage principals, assistant principals, teachers and special services providers in self-reflection on their practice and progress from last year (the self-assessment and reflection should incorporate last year’s evaluation). | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Revisit Educator Evaluation Professional Goals | Revisit educator evaluation professional goals with any teachers or SSPs you may have missed at the end of last year. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Support evaluators and educators in evaluation process | Train and support evaluators and educators in the upcoming evaluation process as needed (e.g., ensure understanding of evaluation processes, measures of student learning/outcomes [MSLs/MSOs] to be used for the 2022-23 school year, inter-rater agreement, and connections to district and school initiatives.) | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Elementary
Quarter 1 | Kindergarten School Readiness | Plan for implementation of school readiness assessment and plans. | Elementary | 2022-07-01 | 2022-08-30 | 43d
Quarter 1 | Colorado READ Act | Plan for READ assessment process. | Elementary | 2022-07-01 | 2022-08-30 | 43d
Quarter 1 | Colorado READ Act | Check the READ Act and School Readiness webpages for upcoming training information. | Elementary | 2022-07-01 | 2022-08-30 | 43d
Quarter 1 | Colorado READ Act | Ensure all K-3 students have been assessed for significant reading deficiencies and individual READ plans are initiated and/or revised as needed (READ Act). | Elementary | 2022-07-01 | Within 90 days from the first day of school | 66d
Quarter 1 | Conduct School Readiness Assessments and Implement Plans | Support kindergarten teachers with school readiness plan and assessment process. | Elementary | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Conduct READ Assessments and Implement Plans | Ensure all K-3 students have been assessed for significant reading deficiencies and individual READ plans are initiated and/or revised as needed (READ Act). | Elementary | 2022-07-01 | 2022-09-30 | 66d
Schools of Choice
Quarter 1 | Charter Policy to Request Paper Form of State Assessment | Charter principals: Adopt and implement a written policy by which the local education provider (i.e. school) will decide whether to request the paper form of the state assessments. Policy is to be distributed to parents and posted to the school website "before the start of fall semester classes." | Schools of Choice | 2022-07-01 | 2022-09-01 | 45d
Quarter 1 | Charter Communication on Assessment Schedule | Charter principals: Distribute and post written information regarding the assessments to be administered during the school year including an assessment calendar (recommendation: "as early as possible" and coordinate first with authorizer). | Schools of Choice | 2022-07-01 | 2022-12-30 | 131d
Quarter 1 | Charter Policy for Student Excusal from State Assessments | Charter principals: Adopt and implement a written policy and procedure by which a student’s parent(s) may excuse the student from participating in one or more of the state assessments. (recommendation: coordinate first with authorizer). | Schools of Choice | 2022-07-01 | 2022-12-30 | 131d
UIP
Quarter 1 | Implement UIP and Monitor Progress | Implement action plan in school UIP. Review interim measures and implementation benchmarks and adjust plan accordingly. Ensure accountability committee is involved in quarterly reviews. | UIP | 2022-07-01 | 2023-06-30 | 261d
| Quarter Two Actions |  |  | 2022-10-01 | 2022-12-30 | 66d
Accountability
Quarter 2 | Transitional Frameworks Finalized | Plan types not submitted for Request to Reconsider finalized and reviewed by the State Board of Education for approval at the November meeting. Remainder of plans types approved by the State Board of Education finalized at the December meeting. | Accountability | 2022-11-10 | 2022-12-15 | 26d
Assessment
Quarter 2 | Verify Requests for Extended CMAS (Math and ELA) Testing Windows Have Been Submitted | Verify that requests for extended CMAS Mathematics and ELA online testing windows needed to accommodate for technology capacity have been submitted by Dec. 15. CMAS Mathematics and ELA testing should be completed during the three week window in April with extensions requested only in those cases when district technology capacity requires additional online testing groups that prevents testing from being completed in that window. | Assessment | 2022-10-03 | 2022-12-15 | 54d
Quarter 2 | Verify Requests for Early High School CMAS (Science) Testing Windows Have Been Submitted. | Verify that requests for early testing windows for high school CMAS Science have been submitted by Dec. 15. | Assessment | 2022-10-03 | 2022-12-15 | 54d
Quarter 2 | Verify Unique Accommodation Requests Have Been Submitted | Verify that Unique Accommodations Requests, if needed, have been submitted by Dec. 15. | Assessment | 2022-10-03 | 2022-12-15 | 54d
Quarter 2 | Verify Testing Centers for PSAT and SAT | Verify that high schools have been established as testing centers for PSAT and SAT. Online schools will need to identify brick-and-mortar sites for school day testing. | Assessment | 2022-10-03 | 2022-12-30 | 65d
Quarter 2 | Verify Vouchers for Online Students Have Been Ordered | Verify vouchers have been ordered for online students for whom appropriate school day testing sites cannot be identified. | Assessment | 2022-10-03 | 2022-12-30 | 65d
Quarter 2 | Track Requests for PSAT and SAT Accommodations | Verify that staff have begun to request PSAT and SAT accommodations. | Assessment | 2022-10-03 | 2022-12-30 | 65d
Educator Effectiveness
Quarter 2 | Submit Final Educator Evaluation Ratings from 2021-22 school year | Submit final 2021-22 educator evaluation ratings for all licensed personnel, whom you have evaluated, to your district for inclusion in the HR collection to CDE. | Educator Effectiveness | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Ensure evaluators conducting observations in support of educator evaluations | Ensure all supervisors/evaluators of licensed personnel (i.e., teachers, SSPs, and principals/assistant principals) are conducting and calibrating observation data aligned with school/district practices and corresponding standards and elements, as well as providing ongoing/timely feedback to educators. Identify initial areas of educator strength, opportunities for growth, and any support needed. | Educator Effectiveness | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Participate in district review of Educator Evaluation System | Participate in district review of current evaluation system with supervisors/evaluators to identify areas for improvement/refinement, as well as identify areas that will require system wide updates per SB22-070 for the 2023-24 school year. | Educator Effectiveness | 2022-10-01 | 2022-12-30 | 66d
Elementary
Quarter 2 | Colorado READ Act | Determine dates for end-of-year conferences for students with a significant reading deficiency. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Colorado READ Act | Ensure all kindergarten students have an individual school readiness plan. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Colorado READ Act | Determine dates for end-of-year conferences for students with a significant reading deficiency. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Colorado READ Act | Ensure all kindergarten students have an individual school readiness plan. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Colorado School Readiness | Ensure school readiness data collection information is ready for district submission. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Submit School Readiness Data | Ensure school readiness data collection information is ready for district submission. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Schools of Choice
Quarter 2 | Collect Charter School Renewal Applications | No later than December 1 of the year prior to the year in which a charter school contract expires, the charter board shall submit a renewal application to the local board of education. | Schools of Choice | 2022-09-01 | 2022-12-01 | 66d
Standards
Quarter 2 | Assess Professional Development Needs in Implementing Revised CO Academic Standards | Principals should monitor educators understanding of the revisions to the 2020 Colorado Academic Standards to assess budgetary and professional development needs. | Standards | 2022-10-01 | 2022-12-30 | 66d
UIP
Quarter 2 | Submit UIPs for Public Posting | Submit updated school and UIPs for public posting on SchoolView. Consider requirements around local board approval of plans for schools on Priority Improvement or Turnaround. CDE will review plans for schools with Priority Improvement, Turnaround and ESSA CS identifications. Note school/district with a Performance plan type may qualify for biennial flexibility. | UIP | 2022-10-25 | 2022-11-02 | 7d
| Quarter Three Actions |  |  | 2023-01-01 | 2023-03-31 | 66d
Assessment
Quarter 3 | Prepare Technology Environments | Verify that technology environments have been prepared for all computer-based state testing. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Administer ACCESS for English Language Learners | Administer ACCESS for English Language Learners. | Assessment | 2023-01-09 | 2023-02-10 | 25d
Quarter 3 | Verify CMAS Paper Materials Have Been Requested | Verify any needed CMAS paper materials, including accommodation materials, have been requested (expected deadline: Jan. 27, 2023). | Assessment | 2023-01-02 | 2023-01-27 | 20d
Quarter 3 | Verify Completion of State Assessment Training and Security Agreements | Verify that District Assessment Coordinators have scheduled and/or conducted state assessment administration training for staff and that security agreements have been signed and collected. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Verify Student CMAS Registrations and Create Computer-Based Sessions | Verify that student CMAS registrations have been updated as appropriate and that computer-based test sessions have been created as needed. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Assign CMAS Special Forms | Verify that staff have assigned CMAS special forms in PearsonAccessnext (e.g., accommodations, text-to-speech) as appropriate. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Submit Accommodations to College Board for PSAT/SAT | Verify that staff have submitted accommodations information to College Board for PSAT/SAT (January (exact date TBD) for College Board approved and February (exact date TBD) for state-allowed). | Assessment | 2023-01-02 | 2023-02-28 | 42d
Quarter 3 | Communicate about Optional SAT Essay | Verify that high schools have distributed information about the optional SAT Essay to students and have facilitated registration for the SAT Essay for any students who want to take it. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Communicate about Optional Questionnaire for PSAT 10 and SAT | Verify that high schools have distributed information to students and parents and have obtained consent for those students who want to participate in the optional questionnaire for PSAT 10 and SAT. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Verify Data Respondents | Verify that data respondents have been assigned for all Student Biographical Data reviews. | Assessment | 2023-01-02 | 2023-05-05 | 90d
Educator Effectiveness
Quarter 3 | Mid-Year Reflection and conversation between evaluator and educator | Supervisors/evaluators of licensed personnel (teachers, SSPs, and principals/assistant principals) have a mid-year conference to reflect on educator evaluation observations, data/evidence collected to date, discuss feedback and highlight areas of strength and needed growth. Make any adjustments to goals if needed. After mid-year review supervisors continue to conduct observations, collect evidence and give ongoing feedback for all teachers and SSPs throughout the year. | Educator Effectiveness | 2022-12-01 | 2023-03-29 | 85d
Elementary
Quarter 3 | Identify School Readiness Training Needs | Determine training needs for kindergarten teachers for school readiness plans and assessment. | Elementary | 2023-01-01 | 2023-03-29 | 64d
Quarter 3 | Ensure Staff are Participating in READ Training | Ensure K-3 educators are particicipating in an evidenced based training required under the READ Act. | Elementary | 2023-01-01 | 2023-03-29 | 64d
Standards
Quarter 3 | Identify Gaps in Resources Aligned to 2020 CO Academic Standards | Principals should provide educators with time to identify any potential gaps in materials and resources alignment when aligned to 2020 Colorado Academic Standards. | Standards | 2023-01-01 | 2023-03-29 | 64d
| Quarter Four Actions |  |  | 2023-04-01 | 2023-06-30 | 66d
Assessment
Quarter 4 | Administer CMAS and CoAlt Assessments | Administer CMAS and CoAlt assessments. | Assessment | 2023-04-10 | 2023-04-28 | 15d
Quarter 4 | Administer PSAT and SAT | Administer PSAT for 9th- and 10th graders; SAT for 11th graders. | Assessment | 2023-04-12 | 2023-04-28 | 13d
Quarter 4 | Verify Demographic Information | Verify demographic information for all state content assessments is updated in vendor systems as appropriate. | Assessment | 2023-04-01 | 2023-05-12 | 31d
Quarter 4 | Review Student Biographical Data (SBD) | Participate in Student Biographical data (SBD) review for assessments. | Assessment | 2023-04-01 | 2023-06-09 | 51d
Quarter 4 | Review Individual Student Level Data from 2022 Assessments | Review individual student-level data from the 2023 state assessments as they become available. | Assessment | 2023-04-03 | 2023-07-28 | 85d
Educator Effectiveness
Quarter 4 | Finish Educator Evaluations and Set Preliminary Goals for Next Year | Finish all educator evaluation observations and evidence collection for teacher and SSP evaluations. Hold end-of-year conferences to report on the near-final evaluation rating. Present final written report and preliminary rating two weeks prior to the end of the school year. Set preliminary goals for next year. | Educator Effectiveness | 2023-04-01 | 2023-06-30 | 66d
Elementary
Quarter 4 | Colorado READ Act | Ensure all K-3 students have been assessed with end of year assessments. | Elementary | 2023-04-01 | 2023-06-16 | 56d
Quarter 4 | Colorado READ Act | Ensure all K-3 students on READ plans have had their end of year conferences. | Elementary | 2023-04-01 | 2023-06-16 | 56d
Quarter 4 | Ensure Staff are Participating in School Readiness Training | Register kindergarten teachers for school readiness assessment training as needed. | Elementary | 2023-04-01 | 2023-06-16 | 56d
Quarter 4 | Submit READ Data | Ensure READ data collection information is submitted to district. | Elementary | 2023-04-01 | 2023-06-16 | 56d
Quarter 4 | Ensure Staff are Participating in READ Training | Ensure K-3 educators are particicipating in an evidenced based training required under the READ Act. | Elementary | 2023-04-01 | 2023-06-16 | 56d
Secondary
Quarter 4 | Report Graduation Guidelines through Year-End Report | Work with data responders, counselors, and teachers to report the Graduation Guidelines measures that all high school students have met, especially seniors with AYG 2022 and 5th year seniors with AYG 2021. | Secondary | 2023-04-01 | 2023-06-29 | 65d
Standards
Quarter 4 | Address Curricular Gaps to Meet 2020 CO Adademic Standards | Principals should provide educators with time in creating a curricular scope and sequence to the 2020 Colorado Academic Standards to assist educators in addressing any curricular gaps in the coming school year. | Standards | 2023-04-01 | 2023-06-16 | 56d
UIP
Quarter 4 | Improvement Planning for 2023-24 | Review local data and begin adjusting UIP for next school year. Include stakeholders (e.g., accountability committee). State data in fall 2023 can be used to validate performance challenges and root causes, when available. | UIP | 2022-04-01 | 2022-06-30 | 65d