## Superintendent Integrated Timel
Quarter | Task Name | Description | Topic | Start | Finish | Duration | Predecessors | Assigned To | % Complete | Status | Comments | Column13 | Column14
| Quarter One Actions |  |  | 2022-07-01 | 2022-09-30 | 66d
| Accountability |  |  |  |  | 295d
Quarter 1 | Preliminary Transitional Frameworks Release | Analyze 2022 preliminary School and District Transitional Frameworks (expected availability in late August for traditional schools). Reports and data will be provided to district accountability contacts via Syncplicity. | Accountability | 2022-09-02 | 2022-12-02 | 66d
Quarter 1 | ESSA Improvement Identification Release | Analyze data for schools identified under the Every Student Succeeds Act (ESSA) for Comprehensive Support and Improvement (CS), Targeted Support and Improvement (TS) or Additional Targeted Support and Improvement (ATS). | Accountability | 2022-08-30 | 2022-09-05 | 5d
Quarter 1 | District Accreditation Contract | Review and sign district accreditation contract (superintendent and board president). Note: Applies just to districts that are on an annual cycle (i.e., Improvement, Accountability Clock, Insufficient State Data) or choose to sign annually. | Accountability | 2022-08-24 | 2023-08-24 | 262d
Quarter 1 | AEC Performance Frameworks Release | Analyze 2022 AEC Transitional Frameworks (expected availability mid-September). Reports and data will be provided to district accountability contacts via Syncplicity. | Accountability | 2022-09-15 | 2023-11-01 | 295d
Quarter 1 | Identify District Accountability Contact | Identify and submit your district's accountability contact to receive accountability updates throughout the year and data files (e.g., growth data). | Accountability | 2022-07-01 | 2022-07-13 | 9d
Quarter 1 | Accountability Committee Involvement in UIP and Budget | Ensure District and School Accountability Committees are involved in revising the UIP and providing input on budgets. | Accountability | 2022-07-01 | 2022-09-27 | 63d
Quarter 1 | Expected Request to Reconsider Window | Districts may provide additional evidence if they do not agree with the preliminary 2022 plan type or wish apply to exit the district/school from the accountability clock. New 90% total state participation rate threshold applies. | Accountability | 2022-09-02 | 2022-10-25 | 38d
| Assessment |  |  |  |  | 67d
Quarter 1 | Identify District Assessment Coordinator and District Technology Coordinator | Ensure your district has an appointed district assessment coordinator and district technology coordinator. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Develop a Policy to Request Paper Form of State Assessment | Adopt and implement a written policy by which the local education provider will decide whether to request the paper form of the state assessments. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Communicate Assessment Schedule to Public | Distribute and post written information regarding the assessments to be administered during the school year including an assessment calendar. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Develop a Policy for Student Excusal from State Assessment Participation | LEPs: Adopt and implement a written policy and implement LEP’s procedure by which a student’s parent(s) may excuse the student from participating in one or more of the state assessments. | Assessment | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Share 2021 Individual State Assessment Results | Distribute 2022 state assessment results to educators and parents. Confidential individual student reports can be shared with parents as soon as they are available. Aggregated and individual student level results may be used internally for informational planning purposes before results are publicly released. | Assessment | 2022-06-17 | 2022-09-30 | 76d
Quarter 1 | Update Student Demographic Data | Update student interchange with accurate demographic data in preparation for initial pre-ID rostering of ACCESS for ELLs (November), CMAS/CoAlt (based on October count data) and PSAT grades 9 & 10 and SAT (based on October count data) assessments. | Assessment | 2022-09-01 | 2022-12-15 | 76d
| Data Collections and Grants |  |  |  |  | 66d
Quarter 1 | Prior Year End of Year Data | Finalize End of Year data. | Data Collections and Grants | 2022-05-05 | 2022-12-01 | 151d
Quarter 1 | Submit Eligibility Form for Library Materials | Ensure the district has submitted the two-page eligibility form by Sept. 15 for its share of state formula grants for print and online library materials. | Data Collections and Grants | 2022-07-01 | 2022-09-15 | 55d
| Educator Effectiveness |  |  |  |  | 67d
Quarter 1 | Performance Management System Updates | For LEAs using the Colorado Performance Management System (COPMS) in RANDA: Identify person(s) responsible for tech support and Local Access Manager (LAM); disable all accounts for educators no longer employed by the district; enable the new school year and update educator roles and assigned evaluators within COPMS. | Educator Effectiveness | 2022-07-13 | 2022-09-01 | 37d
Quarter 1 | Stakeholder Engagement | Identify key stakeholders to participate in district Advisory Personnel Performance Evaluation Council (also known as "1338 Council") for planning and review of district educator evaluation system and practices. NOTE: Advisory Personnel Performance Evaluation Councils (1338 Councils) can be composed of any other school district committee that meets the requirements of membership such as District Accountability Committees. This council must consult with the local school board as to the fairness, effectiveness, credibility, and professional quality of local evaluation systems, processes and procedures. | Educator Effectiveness | 2022-07-01 | 2022-09-01 | 45d
Quarter 1 | Evaluation System Training for New Educators | Provide a full and comprehensive training on the district's evaluation system and practices for all new licensed personnel (i.e., teachers, special services providers [SSPs], principals, and assistant principals). | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Orient Returning Educators on Educator Evaluation System Changes | Provide re-orientation training for all licensed personnel (i.e., teachers, SSPs, principals, and assistant principals) on the district's educator evaluation system and highlight any updates/adjustments in process or measures of student learning/outcomes that will take place for the school year. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Revisit Educator Evaluation Professional Goals | Revisit educator evaluation professional goals with any principals and district personnel that you may have missed at the end of last year. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Ensure school leaders are prepared to support educators in evaluation process | Work with principals to make sure that they are prepared to train and support educators in the upcoming evaluation process (e.g., common understanding of evaluation processes, inter-rater agreement, and connections to district and school initiatives) | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Finalize district-level decisions related to measures of student learning/ outcomes (MSL/MSOs) | Work with members of district's Advisory Personnel Performance Evaluation Council (1338 Council) to determine percentages of collective and individual measures to be included within the MSL/MSO portion of educators' evaluation for the 2022-23 school year. | Educator Effectiveness | 2022-07-01 | 2022-09-30 | 66d
| Elementary |  |  |  |  | 67d
Quarter 1 | Conduct School Readiness Assessments and Implement Plans | Ensure elementary principals implement school readiness plans and assessments for kindergartners. | Elementary | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Conduct READ Assessments and Implement Plans | Ensure elementary principals implement READ Act assessments. | Elementary | 2022-07-01 | 2022-09-30 | 66d
Quarter 1 | Evidence based training in reading | Submit evidence indicating that all K-3 teachers have completed the evidence-based training in reading | Elementary | 2022-07-01 | 2022-08-31 | 44d
Quarter 1 | Implement Plan to Train K-3 Educators for READ Act | Implement a plan to allow new to school and new to grade K-3 educators to complete the evidenced based training program under the READ Act | Elementary | 2022-07-01 | 2023-08-01 | 283d
Schools of Choice
Quarter 1 | Authorizer Assurances for New Online Schools/Programs | Sept. 20, 2022- Deadline for Authorizer Assurances for districts with new online schools or programs *Note: Districts with existing online schools and/or programs should review existing Authorizer Assurances and policies to ensure they are current. Authorizer Assurances for existing online schools and/or programs only need to submit if policies have been updated. | Schools of Choice | 2022-07-01 | 2022-09-20 | 58d
Quarter 1 | Charter School Applications Filed | Charter school applications must be filed with an authorizer not earlier than August 1 or later than October 1 unless the district has an approved waiver on the application deadline from CDE. Time restrictions concerning the review of an application can be found in 22-30.5-107, C.R.S. | Schools of Choice | 2022-08-01 | 2022-09-30 | 45d
Quarter 4 | Review Charter Schools' Performance | During the term of a charter school contract, the school district shall annually review the charter school’s performance – to include the charter school's progress toward meeting objectives and financial audit (note: this can be done at any time in the year. | Schools of Choice | 2022-07-01 | 2023-06-30 | 261d
| Secondary |  |  |  |  | 66d
Quarter 1 | Align Graduation Requirements with Graduation Guidelines | Ensure that your local school board has aligned Graduation Guidelines with your Graduation Requirements. | Secondary | 2022-07-01 | 2022-09-27 | 63d
Quarter 1 | Implement and Communicate Graduation Requirements | Continue to meet with your Graduation Guidelines team to design and implement district graduation requirements. for the class of 2021. Note that Graduation Guidelines goes into effect for students graduating in the 2021-22 school year, including 5th years from AYG 2021 and all students with AYG 2022 and beyond, including 3-year graduates. | Secondary | 2022-07-01 | 2022-09-27 | 63d
Quarter 1 | Determine and Communicate Concurrent Enrollment Opportunities | Develop (or update) a district or authorizer policy for concurrent enrollment that states what types of courses will be approved and not approved and the eligibility conditions for qualified students for concurrent enrollment | Secondary | 2022-07-01 | 2022-09-27 | 63d
| UIP |  |  |  |  | 66d
Quarter 1 | Implement UIP and Progress Monitor | Implement action plan in district UIP and ensure that schools are implementing their action plans. Review interim measures and implementation benchmarks and adjust plan accordingly. Ensure accoutability committee is involved in quarterly reviews. | UIP | 2022-07-01 | 2022-09-27 | 63d
Quarter 1 | Support Schools Identified for Improvement through State and Federal Accountability | Support any schools on the accountability clock (PI, Turnaround) or identified through ESSA (CS, TS, ATS) meet additional requirements (e.g., additional UIP requirements) and consider additional supports (e.g., EASI application). | UIP | 2022-07-01 | 2022-08-04 | 25d
Quarter 1 | Review data from Colorado TLCC Survey | Analyze data from TLCC Survey and consider ways to use information for school improvement (e.g., include as a data source in UIP). | UIP | 2022-07-01 | 2023-06-30 | 261d
| Quarter Two Actions |  |  | 2022-10-01 | 2022-12-30 | 66d
| Accountability |  |  |  |  | 22d
Quarter 2 | Transitional Frameworks Finalized | Plan types not submitted for Request to Reconsider finalized and reviewed by the State Board of Education for approval at the November meeting. Remainder of plans types approved by the State Board of Education finalized at the December meeting. | Accountability | 2022-11-10 | 2022-12-15 | 26d
| Assessment |  |  |  |  | 67d
Quarter 2 | Verify Requests for Extended CMAS (Math and ELA) Testing Windows Have Been Submitted | Verify that requests for extended CMAS Mathematics and ELA online testing windows needed to accommodate for technology capacity have been submitted by Dec. 15. CMAS Mathematics and ELA testing should be completed during the three week window in April with extensions requested only in those cases when district technology capacity requires additional online testing groups that prevents testing from being completed in that window. | Assessment | 2022-10-01 | 2022-12-15 | 55d
Quarter 2 | Verify Requests for Extended CMAS (Science) Testing Windows Have been Submitted | Verify that requests for early testing windows for high school CMAS Science have been submitted by Dec. 15. | Assessment | 2022-10-03 | 2022-12-15 | 54d
Quarter 2 | Verify Unique Accommodation Requests Have Been Submitted | Verify that Unique Accommodations Requests, if needed, have been submitted by Dec. 15. | Assessment | 2022-10-03 | 2022-12-15 | 54d
Quarter 2 | Verify Testing Centers for PSAT and SAT | Verify that high schools have been established as testing centers for PSAT and SAT. Online schools will need to identify brick-and-mortar sites for school day testing. | Assessment | 2022-10-03 | 2022-12-30 | 65d
Quarter 2 | Verify Vouchers for Online Students Have Been Ordered | Verify vouchers have been ordered for online students for whom appropriate school day testing sites cannot be identified. | Assessment | 2022-10-03 | 2022-12-30 | 65d
Quarter 2 | Track Requests for PSAT and SAT Accommodations | Verify that staff have begun to request PSAT and SAT accommodations. | Assessment | 2022-10-03 | 2022-12-30 | 65d
| Data Collections and Grants |  |  |  |  | 66d
Quarter 2 | Human Resources Data | Submit HR data. | Data Collections and Grants | 2022-11-02 | 2023-04-27 | 127d
Quarter 2 | Submit EASI Application | If eligible, submit application for EASI (Empowering Action for School Improvement) grant funds and school improvement services. | Data Collections and Grants | 2022-10-01 | 2022-12-09 | 51d
| Educator Effectiveness |  |  |  |  | 66d
Quarter 2 | Submit Final Educator Evaluation Ratings from 2021-22 school year | Submit final 2021-22 overall educator final evaluation ratings and standard level evaluation ratings to CDE for all licensed personnel including teachers, SSPs, principals, and assistant principals in the HR collection. | Educator Effectiveness | 2022-10-01 | 2022-12-14 | 54d
Quarter 2 | Conduct a review of current Educator Evaluation System | Review current evaluation system with supervisors/evaluators to identify areas for improvement/refinement, as well as identify areas that will require system wide updates per SB22-070 for the 2023-24 school year. | Educator Effectiveness | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Ongoing Observations and Feedback | Supervisors/evaluators provide ongoing observations and feedback as a part of the evaluation cycle for all teachers, SSPs, principals, and assistant principals. | Educator Effectiveness | 2022-10-01 | 2022-12-30 | 66d
| Elementary |  |  |  |  | 66d
Quarter 2 | Create and Implement READ Plans | Ensure elementary principals have supported diagnostic reading assessments for students identified with a significant reading deficiency and the creation of individual READ plans. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Implement School Readiness Plans | Monitor implementation of school readiness plans and assessments. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Submit Kindergarten School Readiness Data | Submit Kindergarten School Readiness data collection. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Ensure K-3 Educators Participate in READ Act Evidence Based Training Program | Ensure a plan is in development to allow K-3 educators to complete the evidenced based training program under the READ Act | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Colorado READ Act | Ensure elementary principals have supported diagnostic reading assessments for students identified with a significant reading deficiency and the creation of individual READ plans. | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | School Readiness | Monitor implementation of school readiness plans and assessments | Elementary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | School Readiness | Submit Kindergarten School Readiness data collection. | Elementary | 2022-10-01 | 2022-12-30 | 66d
| Schools of Choice |  |  |  |  | 66d
Quarter 2 | Collect Charter School Renewal Applications | No later than December 1 of the year prior to the year in which a charter school contract expires, the charter board shall submit a renewal application to the local board of education. | Schools of Choice | 2022-09-01 | 2022-11-01 | 44d | [5 empty] | kottenstette_b@cde.state.co.us
Quarter 2 | Multi-District Online Certificification Application (1st Option) | Multi-district Online Certification application deadline for districts seeking certification (first option deadline) | Schools of Choice | 2022-10-01 | 2023-01-02 | 67d
| Secondary |  |  |  |  | 66d
Quarter 2 | Communicate Concurrent Enrollment Opportunities | Communicate all concurrent enrollment opportunities to students and families, referencing the district or authorizer policy. | Secondary | 2022-10-01 | 2022-12-30 | 66d
Quarter 2 | Engage Stakeholders on Graduation Requirements | Engage the community and staff members in conversations about your graduation requirements. Inform high school students and families - especially in the class of 2022 - about your revised graduation requirements. | Secondary | 2022-10-01 | 2022-12-30 | 66d
| UIP |  |  |  |  | 66d
Quarter 2 | Submit UIPs for Public Posting | Submit updated school and district UIPs for public posting on SchoolView. Consider requirements around local board approval of plans for schools on Priority Improvement or Turnaround. CDE will review plans for schools/districts with Priority Improvement, Turnaround and ESSA CS identifications. Note school/district with a Performance plan type may qualify for biennial flexibility. | UIP | 2022-10-25 | 2023-01-19 | 63d
| Quarter Three Actions |  |  | 2023-01-01 | 2024-02-28 | 304d
| Assessment |  |  |  |  | 63d
Quarter 3 | Verify CMAS Paper Materials Have been Requested | Verify any needed CMAS paper materials, including accommodation materials, have been requested (expected deadline: Jan. 27, 2023). | Assessment | 2023-01-02 | 2023-01-27 | 20d
Quarter 3 | Submit Accommodations to College Board for PSAT/SAT | Verify that staff have submitted accommodations information to College Board for PSAT/SAT (January (exact date TBD) for College Board approved and February (exact date TBD) for state-allowed). | Assessment | 2023-01-02 | 2023-02-28 | 42d
Quarter 3 | Prepare Technology Environments | Verify that technology environments have been prepared for all computer-based state testing. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Verify Completion of State Assessment Training and Complete Security Agreements | Verify that District Assessment Coordinators have scheduled and/or conducted state assessment administration training for staff and that security agreements have been signed and collected. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Verify Student CMAS Registrations and Create Computer-Based Sessions | Verify that student CMAS registrations have been updated as appropriate and that computer-based test sessions have been created as needed. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Assign CMAS Special Forms | Verify that staff have assigned CMAS special forms in PearsonAccessnext (e.g., accommodations, text-to-speech) as appropriate. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Communicate about Optional SAT Essay | Verify that high schools have distributed information about the optional SAT Essay to students and have facilitated registration for the SAT Essay for any students who want to take it. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Communicate about Optional Questionnaire for PSAT 10 and SAT | Verify that high schools have distributed information to students and parents and have obtained consent for those students who want to participate in the optional questionnaire for PSAT 10 and SAT. | Assessment | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Verify Data Respondents | Verify that data respondents have been assigned for all Student Biographical Data reviews. | Assessment | 2023-01-02 | 2023-05-05 | 90d
Quarter 3 | Administer ACCESS for English language learners. | Administer ACCESS for English Language Learners | Assessment | 2023-01-09 | 2023-02-10 | 25d
| Educator Effectiveness |  |  |  |  | 131d
Quarter 3 | Mid-Year Reflection and conversations between evaluators and educators | Supervisors/evaluators of all licensed personnel (teachers, SSPs, and principals/assistant principals) have a mid-year conference to reflect on educator evaluation observations, data/evidence collected to date, discuss feedback and highlight areas of strength and needed growth. Make any adjustments to goals if needed. Supervisors/evaluators continue to conduct observations, collect evidence and give ongoing feedback for all teachers, SSPs, principals, and assistant principals through the end of the school year. | Educator Effectiveness | 2022-12-01 | 2023-03-02 | 66d
Elementary
Quarter 3 | Colorado READ Act | Monitor K-3 teacher completion of the required teacher training for the READ ACt | Elementary | 2023-01-01 | 2023-03-31 | 66d
| Schools of Choice |  |  |  |  | 131d
Quarter 3 | Multi-District Online Certificification Amendments | Application window for submitting amendment to existing Multi-district Online Certification | Schools of Choice | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Multi-District Online Certificification Application (2nd Option) | Multi-district Online Certification application deadline for districts seeking certification (second option deadline) | Schools of Choice | 2023-01-02 | 2023-03-31 | 65d
Quarter 3 | Local Board Resolution on Charter Renewal Application | The local board shall rule by resolution on the renewal application of a charter school no later than February 1 of the year in which the charter expires (or a mutually agreed upon date). | Schools of Choice | 2022-12-01 | 2023-02-01 | 45d
| Quarter Four Actions |  |  | 2023-03-01 | 2023-06-30 | 88d
| Assessment |  |  |  |  | 63d
Quarter 4 | Verify Demographic Information | Verify demographic information for all state content assessments is updated in vendor systems as appropriate. | Assessment | 2023-04-01 | 2023-05-12 | 31d
Quarter 4 | Review Student Biographical Data (SBD) | Participate in Student Biographical data (SBD) review for assessments. | Assessment | 2023-04-01 | 2023-06-09 | 51d
Quarter 4 | Review Individual Student Level Data from 2022 Assessments | Review individual student level data from 2023 state assessments as they become available. | Assessment | 2023-04-03 | 2023-07-28 | 85d
Quarter 4 | Administer CMAS and CoAlt Assessments | Administer CMAS and CoAlt assessments. | Assessment | 2023-04-10 | 2023-04-28 | 15d
Quarter 4 | Administer PSAT and SAT | Administer PSAT for 9th- and 10th-graders and SAT for 11th graders | Assessment | 2023-04-12 | 2023-04-28 | 13d
| Data Collection and Grants |  |  |  |  | 63d
Quarter 4 | Prior Year End of Year Data | Finalize End of Year data. | Data Collections and Grants | 2023-05-05 | 2023-12-01 | 151d
| Educator Effectiveness |  |  |  |  | 66d
Quarter 4 | Finish Educator Evaluations and Set Preliminary Goals for Next Year | Finish all educator evaluation observations and evidence collection for the evaluation process. Ensure all evaluators conduct end-of-year conferences with their assigned educators to provide report on the final effectiveness rating. Present final written report and rating two weeks prior to the end of the school year. Set preliminary professional growth goals for next year. | Educator Effectiveness | 2023-04-01 | 2023-06-30 | 66d
Quarter 4 | Complete EE Assurances for Educator Evaluations Systems | Complete Educator Effectiveness (EE) Assurances for Written Educator Evaluation Systems by July 1, 2023 to provide assurance that the district/BOCES is meeting all requirements outlined in State Board Rules for Written Evaluation Systems and indicate which evaluation system will be used to evaluate each category of licensed personnel for the 2023-24 school year. | Educator Effectiveness | 2023-04-01 | 2023-06-30 | 66d
| Elementary |  |  |  |  | 66d
Quarter 4 | Colorado READ Act | Submit READ data collection. | Elementary | 2023-04-01 | 2023-06-30 | 66d
Quarter 4 | Colorado READ Act | Submit district READ Act budget request for the coming school year | Elementary | 2023-04-01 | 2023-06-30 | 66d
Quarter 4 | Colorado READ Act | Monitor K-3 teacher completion of the required teacher training for the READ Act. Ensure teachers complete the training prior to the start of the 2022-2023 school year | Elementary | 2023-04-01 | 2023-06-30 | 66d
| Schools of Choice |  |  |  |  | 63d
Quarter 4 | Notification of Intent to Open Single District Online Program | July 1st-Deadline for notification to Office of Blended & Online Learning for districts who intend to operate a single district online program for the next school year | Schools of Choice | 2023-04-01 | 2023-06-30 | 66d
| Secondary |  |  |  |  | 63d
Quarter 4 | Improvement Planning for 2022-23 | Review local data and begin adjusting UIP for next school year. Include stakeholders (e.g., accountability committee). State data in fall 2023 can be used to validate adjustments, when available. | UIP | 2023-04-01 | 2023-06-30 | 66d
| UIP |  |  |  |  | 63d
Quarter 4 | Improvement Planning for 2022-23 | Review local data and begin adjusting UIP for next school year. Include stakeholders (e.g., accountability committee). State data in fall 2023 can be used to validate adjustments, when available. | UIP | 2023-04-01 | 2023-06-30 | 66d