## Slide 1: Streamlined UIP 101
Implementation Milestones and Actions

## Slide 2: Session Outcomes
This video will answer the following questions:
What are Action Steps?
How do strong Implementation Milestones and Action Steps support high quality implementation of strategies?
What are Implementation Milestones?
Notes: This video will answer the following questions:
What are Action Steps?
What are Implementation Milestones?
How do strong Action Steps and Implementation Milestones support high quality implementation of strategies?

## Slide 3: What is an Implementation Benchmark?
Implementation Milestones name specific, measurable adult actions or systems that are key to the implementation of a strategy or initiative. They highlight major milestones for phases in a significant or system-wide change, or points in the rollout by which changes will be implemented.
MAJOR IMPROVEMENT STRATEGY
IM/ IM
IM/ IM
IM/IM-Implementation Milestones/Interim Measures
Notes: What is an Implementation Benchmark?
Unlike Action Steps, Implementation Milestones should be measurable. They should name specific ADULT ACTIONS or SCHOOL (or district) SYSTEMS that are particularly crucial to the strategy. Milestones should highlight major milestones for phases in a significant or system-wide change, or they should highlight points in the strategy rollout by which changes should be implemented.

## Slide 4: What is an Implementation Benchmark?
Implementation Milestones should include the following information:
WHAT will be done
WHO will do it
WHEN it will be done
HOW it will be measured
Notes: Identifying HOW progress will be measured is crucial to identifying whether implementation is on track, or, if off track, how far from the target the current state is. In order to provide strong and meaningful touchpoints that can be reliably used to gauge the roll-out of a strategy, Implementation Milestones must be carefully crafted. A strong Implementation Benchmark identifies WHAT will be done (a task or action), WHO will do it (an actor), WHEN it will be done (a date), and HOW it will be measured (a target measurement). Leaving out any of this information will make it difficult or impossible to use the milestone to gauge progress, or to follow up on missed Milestones. E.g., if a benchmark lacks a target measurement, it will be difficult to determine whether that benchmark has been met or missed. If a benchmark lacks an actor, it will be difficult to determine who needs additional support in their role in implementing a strategy.
Note that these four pieces of information may not all be stated in the milestone, but they should be implied or clear within the school’s context.

## Slide 5: High School Examples
Strategy: Create and implement a data-driven assessment model and calendar.
Milestones: By the end of the first Trimester…
90% of daily lesson plans contain a standards-aligned exit ticket.
95% of teachers participate in all Data Analysis Days.
70% of teachers gather performance evidence to adjust instruction at least three times per week.
Strengths:
✔ Milestones name both measure and metric.
✔ Subsequent Milestones can use same measures in order to track progress over time.
✔ Milestones align to key elements of strategy.
Notes: These are examples of Implementation Milestones for a high school strategy that is focused on Instruction and Assessment.
The particular strengths of these Milestones are that they name both a measure and a metric – that is, what particular activity or output will be measured, and what the expected level of completion is. In the first benchmark, “daily lesson plans” are the measure; “90% containing a standards-aligned exit ticket” is the metric against which performance will be gauged. Another strength of these Milestones is that subsequent Milestones can use the same measures in order to track progress over time. For example, if 70% of teachers gather performance evidence to adjust instruction at least three times per week in the first Trimester, a benchmark for the second trimester might specify that 85% of teachers should be meeting that bar, or that 70% of teachers are gathering evidence FOUR times a week rather than three. A final strength of these Milestones is that they align to and gauge progress on key elements of the strategy. These Milestones will help the school to determine at the end of each trimester whether the strategies identified are truly being implemented as planned.

## Slide 6: Elementary School Examples
Strategy: Develop staff’s social comprehension in order to foster a safe, welcoming, focused and inclusive learning environment.
Milestones: By the end of the first trimester…
Total number of major discipline referrals will fall below 15 for the trimester according to Infinite Campus behavior referrals.
Total number of radio calls will be fewer than 30 calls in a given month and fewer than 75 calls in the trimester.
50% of 3rd - 5th graders will rate themselves in the top 3 categories for each question in the Emotion Regulation student survey.
Strengths:
✔ Milestones name expected level of performance (e.g., number of referrals), rather than naming a list of actions that are either complete or incomplete (e.g., PD occurred).
✔ Milestones draw data from a variety of sources.
Notes: These are examples of Implementation Milestones for an elementary school strategy that is focused on building social comprehension creating a safe and focused learning environment.
The particular strengths of these Milestones are that they name an expected level of performance, rather than simply naming a checklist of actions that will either be complete or incomplete. For example, the first benchmark names a specific maximum number of referrals that will indicate that the school’s strategy is being put into practice effectively. A non-example for this same strategy might simply indicate that teachers have received professional development by the end of the trimester. While this development is part of the strategy itself, the simple fact that PD is delivered won’t give the school nuanced information about whether practices are truly changing at the teacher-level. Another strength of these Milestones is that they draw data from a variety of sources, enabling the school to establish a holistic evaluation of the quality of implementation throughout the year.

## Slide 7: Common Misconceptions
Interim Measures
Implementation Milestones
Action Steps
Look at student outcomes
Measure how student performance outcomes are changing
Tell us whether our strategy is effective.
Look at adult actions and systems
Measure how adult actions and systems are changing or being put into practice
Tell us whether our strategy is being implemented as planned.
Look at specific tasks needed to implement strategy.
Pace out actions needed, who will perform them, and resources available.
vs.
vs.
Notes: Implementation Milestones can sometimes be confused for two other elements of the improvement planning process—Interim Measures and Action Steps—but they differ from each in crucial ways.
Implementation Milestones look at adult actions and systems, and they measure how these actions and systems are changing over the course of the year. Interim Measures specifically look at student outcomes, and measure how student performance is changing over the course of the year.
Implementation Milestones and Interim Measures are both elements of a progress monitoring plan. Milestones measure whether a strategy is being implemented as planned, while interim measures indicate whether or not the strategy is having the intended impact on student outcomes – i.e., whether the strategy itself is effective.
Unlike Implementation Milestones and Interim Measures, Action Steps do not “measure” anything; rather, they pace out and detail the specific tasks or actions that will be needed to implement the strategy.

## Slide 8: What are Action Steps?
Action Steps are the tasks that need to be completed to meet the milestones and bring a Major Improvement Strategy to life.
MAJOR IMPROVEMENT STRATEGY
AS 1
AS 2
AS 3
AS 4
AS 5
AS 6
AS 7
AS 8
AS 9
AS 10
AS 11
AS 12
Notes: What are action steps?
Action Steps are the tasks that need to be completed to meet the milestones and bring a major improvement strategy to life. If the strategy itself describes the key approach to shifting practices and systems in order to address Student Performance Priorities, then the action steps are the detailed activities that must take place during the year in order to ensure that those shifts actually take place.

## Slide 9: High School Example
Strategy: Create and implement a data-driven assessment model and calendar.
Action Steps:
On September 15, administer BOY STAR diagnostic assessment for grades 9-12 to establish baseline performance in Math and English.
On October 5, launch PD to train teachers in the use of classroom and student-based data trackers.
On October 20th, implement a Data Day to reflect on STAR and classroom-level data.
On January 15, administer STAR assessment for grades 9-12 to monitor growth in Math and English.
Strengths:
✔ Name specific and concrete tasks to be accomplished.
✔ Specify dates on which actions will take place.
✔ Align to strategy.
Note: Since these action steps do not name specific actors for these tasks, the school will need to ensure that ownership of these actions is clear.
Notes: This is an example of a set of Action Steps for a high school strategy around data-driven assessment.
The particular strengths of these action steps are that they establish focused and concrete tasks to be completed, they name specific dates by or on which those tasks will be done, and they align clearly to and advance the major improvement strategy.
Note that these action steps do not specify who will complete each of these actions. While this may be understood readily by the school team, the school will need to ensure that ownership of each task is clear in order to avoid gaps in implementation.

## Slide 10: Elementary School Example
Strengths:
✔ Indicate specific actors for each task.
✔ Align to strategy
✔ Include training in key foundational aspects of the strategy to ensure teachers are well-equipped to implement the strategy.
Strategy: Develop staff’s social-emotional competency in order to foster a safe, welcoming, focused and inclusive learning environment.
Action Steps:
On August 5, teachers and staff will attend professional development workshops for key culture programs and practices.
By August 25, teachers will create a plan for how to build relationships with students and families during the first 6 weeks of the school year.
By September 10, teachers will have completed spreadsheet to track likes, dislikes, and key identity markers for each student.
Notes: This is an example of a set of Action Steps for an elementary school strategy around social comprehension and a safe and focused learning environment.
The particular strengths of these action steps are that they name key actors – that is, who is responsible for carrying out the task –, they align clearly to the strategy, and they include training for teachers to ensure they’re well-equipped to implement the strategy and its practices.

## Slide 11: Why Implementation Milestones & Action Steps Matter
Strong implementation Milestones
Anchor progress monitoring that effectively gauges whether the planned strategy is being implemented with fidelity (i.e., as it was intended).
Can also be used as touchpoints from which to backwards plan action steps in the improvement planning process
Well-crafted action steps
Enumerate the actions needed to implement a strategy
Are backwards-planned from Major Improvement Strategies to ensure the strategy will be fully implemented in time to influence student performance outcomes.
Notes: Since Implementation Milestones enable us to monitor whether implementation is happening as planned, they can help us identify issues or gaps in implementation before these gaps begin to influence student outcomes. When Milestones are missed or when challenges arise in meeting them, this signals a need to step back, reflect on the plan as a whole and make mid-course corrections, if these are necessary. Rather than waiting for student outcome data to confirm that progress is not being made, using missed Milestones as an opportunity to adjust improvement efforts enables schools to respond nimbly to their ever-evolving contexts to ensure the strongest possible outcomes for students.
Action Steps, on the other hand, provide the school with an overall road-map for the implementation of the strategy. The strongest action steps are backwards planned from a target date for full-implementation. This allows school teams to focus on the the weekly or even daily tasks needed to shift their practices, while establishing a deliberate pacing of tasks to ensure that the strategy has enough time to impact student outcomes.

## Slide 12: Role of Implementation Milestones & Action Steps in the UIP Process
MAJOR IMPROVEMENT STRATEGY
AS 1
AS 2
AS 3
AS 4
IM/ IM
AS 5
AS 6
AS 7
AS 8
AS 9
AS 10
AS 11
AS 12
IM/ IM
EOY Target
Current Performance
Student Performance Priority
IM/IM-Implementation Milestones/Interim Measures
Notes: Within the larger context of the Unified Improvement Plan (UIP), an analysis of current performance informs the selection of a Student Performance Priority. Aligned to that priority, and End of year Target identifies the expected improvement in outcomes for that performance area over the course of the year.
The major improvement strategy describes the actions and system changes that will be made within the school in order to move the school from current state and meet the end of year Target.
Implementation Milestones identify key milestones in the implementation of a Major Improvement Strategy. These Milestones, together with the Interim Measures of expected student outcomes, make it possible to progress monitor the roll-out of the Major Improvement Strategy and to evaluate whether that strategy is having the intended effect on student outcomes.
Action Steps are the final (and most granular) level of detail in the UIP. These describe the activities that will bring the strategy to life at the daily or weekly level, enabling the school to change its practices, meet the Implementation Milestones and Interim Measures, and finally reach its end of year targets.

## Slide 13: Additional Flexibility: Short-Cycle Plans
MAJOR IMPROVEMENT STRATEGY
AS 1
AS 2
AS 3
AS 4
IM/ IM
1st Short-Cycle Plan
IM/ IM
Schools that use a short-cycle (“90-day”) plan as part of their improvement efforts can upload those plans directly to the UIP system. An uploaded short-cycle plan can replace Action Steps, Implementation Milestones and Interim Measures in the UIP online system (as long as the short-cycle plan contains those elements).
Note: The UIP needs to span the entire school year, so if you’re using short-cycle plans, consider how to enter some Implementation Milestones and Interim Measures in the online system for the latter parts of the year.
IM/IM-Implementation Milestones/Interim Measures
Notes: In addition to the flexibility offered to schools eligible to submit plans biennially, there is an additional flexibility within the UIP system to accommodate short-cycle plans (often called 90-day plans).
These short-cycle plans can be uploaded directly to the online system in place of Implementation Milestones, Interim Measures, and Action Steps AS LONG AS those elements are covered in the short-cycle plan.
If you choose to upload short-cycle plans, be aware that the UIP must span the full plan-posting period. In addition to uploading your short-cycle plans, make sure that you set interim measures and implementation Milestones in the UIP online system that do cover the full plan-posting period (1-2 years). Throughout the plan period, as new 90-day plans are created, upload these to the online system so that your plans remain up to date.

## Slide 14: Thank you for your time! Email any questions to uiphelp@cde.state.co.us
Notes: Thank you for your time!
If you have additional questions, please email uiphelp @ cde . state . co . us.